## Master
TASK ID | DESCRIPTION | OWNER | STATUS | CRITICAL | NOTES | REFERENCE | PROJECT ID | REWORK COUNT
253-1/1/SA00016/1 | Assembly review for mates, interferences, drawings | Pranav Limbachiya | Approved |  |  |  | 253-1
253-1/1/SA00016/2 | Check drawings for major revision | Pranav Limbachiya | Approved |  |  |  | 253-1
253-1/1/SA00016/3 | SUBMIT ECN AFTER TASK 2 | Manan Agrawal | Approved |  |  |  | 253-1
253-1/1/SA00016/4 | NEED TO ADD PE0027757 & PE00010 TO SA ASSEMBLY | Meet Gandhi | Approved |  | NEED TO CHECK WHERE USED FOR PE00011 (IN AF) AND TAKE ACTION ACCORDINGLY | 2026-01-02 | 253-1
253-1/1/SA00016/5 | NEED TO PUT HOLES IN THE ROOF FOR THE NEW EYE BOLTS | Meet Gandhi | Approved |  | MAJOR REVISE/MAKE NEW ACCORDING TO WHERE THE ROOF IS USED | 3 | 253-1
253-1/1/SA00016/6 | INTERFERENCE STUDY | Manthan Patel | Review #2 | YES |  |  | 253-1
253-1/2/SA0032583/1 | COMPLETE ASSEMBLY | Meet Gandhi | Approved |  |  |  | 253-1
253-1/2/SA0032583/2 | MOVE HINGES CIRCLED IN BLUE 1 HOLE LOWER AND HINGES CIRCLED IN RED 1 HOLE HIGHER | Meet Gandhi | Approved |  | THE HINGE ON THE DOOR IS IN THE AW ASSEMBLY, THE HINGE THAT IS ATTATCHED TO THE CORNER POST IS IN THE AS ASSEMBLY | 1 | 253-1
253-1/2/SA0032583/3 | ADD THE METAL BRACKET AND GLASTIC SUPPORT PIECE THAT IS ON THE LOAD SIDE OF THE BREAKER TO THE LINE SIDE AS WELL | Meet Gandhi | Approved |  |  | 2026-02-03 | 253-1
253-1/2/SA0032583/4 | MOVE CIRCLED HINGES LOWER BY 0.031" | Meet Gandhi | Approved |  |  | 4 | 253-1
253-1/2/SA0032583/5 | ADD SPACER BETWEEN BUS AND INSULATIOR | Meet Gandhi | Approved |  |  | 5 | 253-1
253-1/2/SA0032583/6 | REMOVE CIRCLED SPACERS | Meet Gandhi | Approved |  |  | 6 | 253-1
253-1/2/SA0032583/7 | EXTEND GLASTIC SHEET TO THE BOTTOM OF THE SHELF AND ATTATCH TO THE CIRCLED HOLE IN SHELF | Yashpriti Raj | Approved |  |  | 7 | 253-1
253-1/2/SA0032583/7 | PUT ASSEMBLY GE0034382 AT CIRCLED PLACES in MA0032774 assembly | Yashpriti Raj | Approved |  | Look at similar cover on left side for reference | 8 | 253-1
253-1/2/SA0032583/8 | INTERFERENCE STUDY | Sarang Chaudhary | In progress |  |  |  | 253-1
253-1/CLOSEOUT | NEED TO CORRECT REVS FOR PARTS IN SHEET, MINOR REV WORKFLOW | Yashpriti Raj | Approved |  |  |  | 253-1
253-1/MA0032774/1 | NEED TO MODIFY GROUND BAR IN SEC 1 AND CHANGE SOLT ORIENTATION | Meet Gandhi | Approved |  | MPD TO APPROVE MINOR REV OF GROUND BAR |  | 253-1
253-1/MA0032774/2 | NEED TO HAVE CLEARANCE HOLES (BLUE CIRCLES FOR EXAMPLE) IN BARRIER AT PLACES WHERE THE HINGE PLATES/SUPPORT CHANNELS BOLTS TO THE CORNER POST | Meet Gandhi | Approved |  | WILL NEED TO REVISE/MAKE NEW BARRIER ACCORDINGLY. DO THIS TASK AFTER TASK 253-1/2/SA0032583/2 | 1 | 253-1
253-1/MA0032774/3 | ADD A HOLE AT PLACE CIRCLED IN RED AND MOVE THE "TAB" CIRCLED IN BLUE 1 HOLE DOWN | Meet Gandhi | Approved |  | MAJOR REVISE PE00529 | 2 | 253-1
253-1/MA0032774/4 | THE DISTANCE BETWEEN THE BARRIER AND THE BUS BAR MUST BE 1.375" MINIMUM | Meet Gandhi | Approved |  | NEED TO MAKE THE CUTOUT IN THE BARRIER WIDER TO GET 1.375" | 3 | 253-1
253-1/MA0032774/5 | NEED TO PUT CORRECT HARDWARE ASSEMBLY, BLUE = GE0034380, RED = GE0034382, YELLOW = DELETE COMPLETELY | Meet Gandhi | Approved |  | WAITING FOR COMMENTS ON REST ROOF/BARRIERS/RIGHT SIDE COVERS | 6, 7, 8, 9, 10 | 253-1
253-1/MA0032774/6 | ADD RIGHT SIDE COVERS IN MA | Meet Gandhi | Approved |  | ASK PRANAV FOR CORRECT COVERS |  | 253-1
253-1/MA0032774/7 | CORRECT/ADD FINISH TO PARTS | Meet Gandhi | Approved | YES | NEEED TO REVIEW DRAWINGS |  | 253-1
253-1/MA0032774/8 | Do a save as on a00166 and make new GE assembly. Delete part arrowed in Blue, replace part arrowed in purple with 1137030 (check notes) | Yashpriti Raj | Approved |  | Please mate triangle spacer correctly | 12 | 253-1 | 1
253-2/1/SA0030388/1 | PUT CORRECT SPACERS IN HIGHLIGHTED SPACES, 5 HOLE WILL BE 5 HOLE PLATE SPACER | Manthan Patel | Approved |  |  | 1 | 253-2
253-2/1/SA0030388/2 | INTERFERENCE STUDY | Manthan Patel | Approved | YES |  |  | 253-2
253-2/2/SA0032565/1 | REDUCE VISIBLE GAP | Yashpriti Raj | Approved |  |  | 1 | 253-2
253-2/2/SA0032565/2 | INTEREFERENCE STUDY | Yashpriti Raj | Approved | YES |  | 2026-02-03 |  | 1
253-2/3/SA0032566/1 | INTERFERENCE STUDY | Yashpriti Raj | Approved | YES |  | 1,2,3 | 253-2 | 1
253-2/4/SA0029956/1 | FIX VERTICAL CHANNEL | Krishi Jani | Approved |  |  |  | 253-2
253-2/4/SA0029956/2 | Assembly review for mates, interferences, drawings | Krishi Jani | Approved |  |  |  | 253-2
253-2/4/SA0034215/1 | SELECTED PARTS (GLASTIC ANGLE AND GLASTIC BRACKET) ARE NOT MATED PROPERLT | Yashpriti Raj | Approved |  |  | 1
253-2/4/SA0034215/2 | INTEFERENCE STUDY | Yashpriti Raj | Approved | YES | USE SA0029956 AND SA0028902 FOR REFERENCE FOR BREAKER PLACEMENT |  |  | 1
253-2/5/SA0032647/1 | NEED TO ADD NOTCH TO PREVENT HARDWARE INTERFERENCE | Manthan Patel | Approved |  |  | 1
253-2/5/SA0032647/2 | INTERFERENCE STUDY | Sarang Chaudhary | Approved | YES | C PHASE HAS UNDERDEFINDED PARTS |  |  | 1
253-2/CLOSEOUT | NEED TO CORRECT REVS FOR PARTS IN SHEET, MINOR REV WORKFLOW | Meet Gandhi | Approved |  | IN COURT OF MPD |  | 253-2
253-2/CLOSEOUT | DRAWING REVIEW FOR PARTS IN PENDING APPROVAL STATUS | Meet Gandhi | In progress |  |  |  | 253-2
253-2/DRAWINGS | NEED TO CORRECT DRAWINGS FOR PARTS LISTED IN SHEET | Meet Gandhi | Approved |  | Meet - Take help of Sarang and Pranav too |  | 253-2
253-2/MA0032649/1 | DISTANCE BETWEEN BUS BAR AND EDGE OF BARRIER SHOULD BE 1.5" | Yashpriti Raj | Approved |  | IF PART IS "PRODUCTION RELEASED" CHECK "WHERE USED" FOR THE PART AND SEE IF REVISION IS BACKWARD COMPATIBLE | 1 | 253-2
253-2/MA0032649/2 | DISTANCE BETWEEN BUS BAR AND EDGE OF BARRIER SHOULD BE 1.5" | Yashpriti Raj | Approved |  |  | 2 | 253-2
253-2/MA0032649/3 | MOVE DEADFRONT COVERS TO MA LEVEL | Meet Gandhi | Approved |  |  |  | 253-2 | 1
3554-6/1/SA00047/1 | Assembly review for mates, interferences, drawings | Krishi Jani | Approved |  |  |  | 3554-6
3554-6/1/SA00047/2 | Check drawings for major revision | Pranav Limbachiya | Approved
3554-6/1/SA00047/3 | CHANGE ORIENTATION OF BLUE CIRCLED SLOTS TO BE LENGTHWISE AND CHANGE SPACING OF HOLES CIRCLED IN RED TO 1.135" | Sarang Chaudhary | Approved | YES |  | 1 | 3554-6
3554-6/2/SA0033477/1 | Assembly review for mates, interferences, drawings | Manan Agrawal | Approved |  |  |  | 3554-6
3554-6/2/SA0033477/2 | Need to roll back parts/assemblies for SA00048 | Manan Agrawal | Approved |  |  |  | 3554-6
3554-6/2/SA0033477/3 | Make MA for 3554-6 using SA00047 and SA0033477 | Pranav Limbachiya | Approved |  |  |  | 3554-6
3554-6/2/SA0033477/4 | ADD SUPPORT CIRCLED IN RED AT LOCATION CIRCLED IN BLUE. WILL NEED TO ADD HOLE IN BUS BAR AND GLASTIC ANGLE BELOW IT | Pranav Limbachiya | Approved | YES |  | 1 | 3554-6
3554-6/MA0033538 | NEED TO UPDATE FINISH TO POWDER COAT FOR ALL PARTS THAT HAVE AM GREY AS FINISH | Pranav Limbachiya | Approved | YES | CHECK BOM IN PDM | 1 | 3554-6
3554-6/MA0033538/2 | NEED TO MAKE CHANGES AS PER PDF | Pranav Limbachiya | Approved | YES |  |  | 3554-6
3554-6/MA0033538/3 | TURN THE CUTOUT TO A NOTCH (REFER TO PART PE00810, THE BARRIER ABOVE). THE DISTANCE FROM THE FACE OF THE BUSBAR TO THE EDGE OF BARRIER SHOULD BE 1.5". THERE IS A NOTCH FOR THE GROUND BUS AS WELL (SMALLER NOTCH IN THE BARRIER BELOW). MODIFY THAT SO IT LOOKS AS SHOWN | Pranav Limbachiya | Approved | YES |  | 2026-02-03 | 3554-6
4063-2/1/SA0034291/1 | INTEFERENCE STUDY | Sarang Chaudhary | Approved | YES
4063-2/1/SA0034291/2 | REPLACE THE HIGHLIGHTED SPACER WITH 5 HOLE SQUARE SPACER | Sarang Chaudhary | Approved |  | ASK MANTHAN FOR PART NUMBER | 1
4063-2/1/SA0034291/3 | CHANGE ORIENTATION OF SLOTS TO BE LENGTHWISE | Sarang Chaudhary | Approved
4063-2/2/SA0029256/1 | NEED TO REVISE SA AND MAKE AW ASSEMBLY (RED) TALLER, AND BLUE COVER (PE PART) SMALLER. | Meet Gandhi | Approved |  | HOLES NOT LINING UP | 5 | 4063-2 | 1
4063-2/2/SA0029256/2 | DO A SAVE AS ON THE SA AND MAKE A NEW SA, SAVE IT IN CORRECT FOLDER IN PDM | Meet Gandhi | Approved |  | FOLDER - 4063/4063-2/SEC 2 (ALREADY MADE IN PDM) |  | 4063-2
4063-2/2/SA0029256/3 | REVISE UPPER AND LOWER VENT | Meet Gandhi | Approved |  | PART NUMBER AND COMMENT ADDED IN MASTER REVISION REGISTER ALREADY |  | 4063-2
4063-2/2/SA0034306/1 | CHECK THE NEW SA IN SOLDIWORKS | Meet Gandhi | Approved |  | INTERFERENCES, MATES, PATTERNS (LOCAL/MIRROR), HOLE ALIGNMENT. IF ANY PART NEEDS TO CHANGE, DECIDE IF MAJOR REVISION NEEDED OR ELSE MAKE A NEW PART |  | 4063-2
4063-2/2/SA0034306/10 | NEED TO PUT SPACER BELOW GLASTIC ANGLE (SIMILAR TO HIGHLIGHTED SPACER) | Manan Agrawal | Approved |  |  | 8
4063-2/2/SA0034306/10 | ADD PART "EATON IP41 BREAKER GASKET" AT HIGHLIGHTED LOCATION IN SA | Sarang Chaudhary | Approved |  |  | 6
4063-2/2/SA0034306/11 | REPLACE "COPY" OF PART (DESIGN TREE) WITH CORRECT PART. | Sarang Chaudhary | Approved |  |  | 7
4063-2/2/SA0034306/2 | DO A SAVE AS ON AH0029265 AND CONVERT TO 3 LAYERS OF BUS (CURRENTLY IT IS 2). JUST NEED TO ADD ONE MORE OF THE ALREADY PRESENT LAYER | Meet Gandhi | Approved |  | FOR THE NEUTRAL LAYER, THE ARRANGEMENT SHALL BE FLAT-JOG-NEUTRAL CT, JOG (BACK TO FRONT) |  | 4063-2
4063-2/2/SA0034306/3 | REPLACE THE NEW AH IN THE NEW SA | Meet Gandhi | Approved |  |  |  | 4063-2
4063-2/2/SA0034306/4 | THE 3RD LAYER ADDED IN THE NEW AH WILL SIT IN BETWEEN YELLOW AND GREEN HIGHLIGHTED PARTS. THUS, THE PART IN YELLOW WILL NEED TO BE SAVED AS MADE A NEW PART TO DECIREASE THE FLANGE LENGTH BY 0.25" | Meet Gandhi | Approved |  | THIS WILL BE DONE FOR ALL PHASES, NOTE THAT SOME OF THESE L PARTS ARE USED IN MULTIPLE PLACES IN THE SA | 2 | 4063-2
4063-2/2/SA0034306/6 | THE GROUND BUS NEEDS TO ACCOMODATE (3) TA-350 LUGS | Meet Gandhi | Approved |  | USE LATEST TA-350 MODEL AS REFERENCE | 4 | 4063-2
4063-2/2/SA0034306/7 | NEED TO REVISE TOP AND LOWER VENT TO HAVE NOTCHES TO PREVENT HARDWARE INTERFERENCE | Meet Gandhi | Approved |  |  |  | 4063-2
4063-2/2/SA0034306/8 | DELETE LEFT SIDE BARRIERS AND MOVE RIGHT SIDE BARRIERS IN MA ASSEMBLY | Meet Gandhi | Approved |  |  |  | 4063-2
4063-2/2/SA0034306/9 | INTERFERENCE STUDY | Sarang Chaudhary | Approved | YES |  |  | 4063-2
4063-2/3/SA0029594/1 | MAJOR REVISE SA AND AS, AND REPLACE VERTICAL STEEL CHANNELS | Pranav Limbachiya | Approved |  | NEED TO ADD ALL MAJOR REVISIONS IN MASTER REVSIION REGISTER, SHEET IS ADDED ALREADY | 1 | 4063-2
4063-2/3/SA0029594/2 | UPDATE CHASSIS MOUNTING CHANNEL IN AS | Pranav Limbachiya | Approved |  |  | 2 | 4063-2
4063-2/3/SA0029594/3 | NEED TO REVISE TOP AND LOWER VENT TO HAVE NOTCHES TO PREVENT HARDWARE INTERFERENCE | Pranav Limbachiya | Approved |  |  | 3 | 4063-2
4063-2/3/SA0029594/4 | REPLACE STEEL ANGLE AND INSULATOR WITH GLASTIC ANGLE | Pranav Limbachiya | Approved |  | ONLY PUT HOLES WHERE NEEDED IN GLASTIC ANGLE ALWAYS | 5 | 4063-2 | 1
4063-2/3/SA0029594/5 | COMPLETE DRAWINGS OF ECN | Pranav Limbachiya | Approved |  |  |  | 4063-2
4063-2/3/SA0034395/1 | MAKE A NEW AH ASSEMBLY AND AND 3RD LAYER OF BUS | Pranav Limbachiya | Approved |  |  | 4 | 4063-2
4063-2/3/SA0034395/2 | ADD ANOTHER LAYER OF BUS TO THE RUNBACKS | Pranav Limbachiya | Approved | YES | SEE ATTACHED IMAGE FOR A PHASE, DO SIMILARLY FOR B AND C PHASE | 6 | 4063-2
4063-2/3/SA0034395/3 | NEED TO CHECK SPACE FOR NEUTRAL AND GROUND LUGS | Meet Gandhi | Approved |  |  |  | 4063-2
4063-2/3/SA0034395/4 | CHANGES AS PER COMMENTS IN SHEET | Sarang Chaudhary | Approved |  |  |  | 4063-2
4063-2/3/SA0034395/5 | INTEREFERENCE STUDY | Sarang Chaudhary | Approved
4063-2/3/SA0034395/6 | UPDATE HOLE SIZE OF TA-350 AND TA-500 LUGS TO 0.397" | Sarang Chaudhary | Approved |  |  | 7
4063-2/3/SA0034395/7 | SPACER MISSING IN AH ASSEMBLY | Sarang Chaudhary | Approved |  |  | 8
4063-2/CLOSEOUT | NEED TO CORRECT REVS OF PARTS | Meet Gandhi | Approved |  |  |  | 4063-2
4063-2/MA0034397/1 | UPDATE GAUGE TABLE OF PARTS LISTED IN SHEET | Sarang Chaudhary | Approved
4063-2/MA0034397/2 | REBUILD ERRORS IN SEC 1 | Pranav Limbachiya | Approved | YES |  |  | 4063-2
4063-2/MA0034397/3 | UPDATE SLOT ORIENTATION IN ALL GROUND BARS | Pranav Limbachiya | Approved |  |  |  | 4063-2
4063-2/MA0034397/4 | DELETE ALL EYE BOLTS (CIRCLED IN BLUE), REPLACED ROOF IN RED WITH PE00264 AND REPLACE ROOF IN GREEN WITH PE0030272. AFTER REPLACING, DELETE PARTS THAT WERE REPLACED | Pranav Limbachiya | Approved |  |  | 2026-01-04 | 4063-2
4063-2/MA0034397/5 | PUT PART PE00165 IN PLACES CIRCLED IN GREEN, AND PART PE00254 AND PLACES CIRCLED IN RED | Pranav Limbachiya | Approved |  | REFER TO MA0030271 FOR MATE REFERENCES | 2026-02-03 | 4063-2
4063-2/MA0034397/6 | MOVE DEADFRONT COVERS TO MA LEVEL | Manan Agrawal | Approved
4063-2/MA0034397/7 | NEED TO ADD BARRIERS BETWEEN SEC 1 AND SEC 2 | Manan Agrawal | In progress |  | VERIFY IF NEEDED WITH MPD. BOTTOM PART NUMBER IS PE0028693 |  | 4063-2
ECN/1 | ECNS IN SHAREPOINT FOR "GAUGE TABLE UPDATES" AND "MA0033538" AND "SA0032647-1" | Yashpriti Raj | In progress |  |  |  | ECN
ECN/2 | REJECT AND CHANGE REV IN DRAWING TO 3.1 | Yashpriti Raj | Approved |  | PB01260 | 1 | ECN
ECN/3 | REJECT AND CHANGE REV IN DRAWING TO 3.1 | Yashpriti Raj | ON-HOLD |  |  | 2 | ECN
GAUGE TABLE/1 | MAKE SURE REVS ARE CORRECT IN PDM | Manan Agrawal | Approved | YES |  |  | GAUGE TABLE
MINOR REV/1 | CHANGE FINISH OF PART PE00490 TO POWDER COAT | Yashpriti Raj | Approved |  |  |  | MINOR REV

## Dashboard
| TOTAL TASKS ASSIGNED | ACTIVE TASKS (IN PROGRESS) | NUMBER OF REWORKS | CRITICAL TASKS ASSIGNED | QUALITY | ENTER PROJECT NUMBER
Manan Agrawal | 7 | 1 | 0 | 1 | 1 | 4063-2
Krishi Jani | 3 | 0 | 0 | 0 | 1
Meet Gandhi | 31 | 1 | 2 | 1 | 0.93939 | STATUS | Number of Tasks
Pranav Limbachiya | 19 | 0 | 1 | 6 | 0.95 | Approved | 25
Sarang Chaudhary | 14 | 1 | 1 | 4 | 0.93333 | In progress | 1
Yashpriti Raj | 15 | 1 | 4 | 3 | 0.78947
Manthan Patel | 4 | 0 | 0 | 2 | 1
need to archive completed tasks but still track in this sheet for quality score

## Quality History
Date | Krishi Jani | Pranav Limbachiya | Meet Gandhi | Sarang Chaudhary | Yashpriti Raj | Manthan Patel
2026-06-06 17:26 | 0.44444 | 0.4 | 0.66667
2026-06-22 15:55 | 1 | 1 | 0.91667
2026-06-27 17:26 | 1 | 0.93333 | 0.95833
2026-07-04 17:26 | 1 | 0.95 | 0.96552 | 1
2026-07-08 19:06 | 1 | 0.95 | 0.93939 | 0.93333 | 0.78947 | 1